## Sheet1
Milestone | Deadline | Tasks (Code) | Tasks (Documentation)
Revision 0 Demonstration | Feb 3 – Feb 14 | - Implement foundational modules: | Describe the purpose of foundational modules. Write an overview of functionality and initial design.
- Oleg: Databases (Label, ImageObject, Labeller) and connectors.
- Kartik and Kyle: Backend APIs for connectors.
- Mathew: Frontend for basic database interactions.
V&V Report Revision 0 | March 7 | - Begin core services implementation: | Document module-level testing strategies. Include high-level testing results. Update SRS and V&V plans.
- Kartik and Kyle: Label Server.
- Oleg: Database and API integration testing.
- Mathew: Develop basic UI for Label Server interactions.
Final Demonstration (Rev 1) | March 24 – March 30 | - Complete core services: | Document core service implementations and integration steps. Update diagrams and traceability matrices.
- Kartik and Kyle: Object Extraction Manager, Image Service Manager.
- Oleg: Optimize database queries for scalability.
- Mathew: Build advanced frontend for services.
EXPO Demonstration | April TBD | - Implement specialized services: | Create presentation materials. Include screenshots, results, and use cases for EXPO demo.
- Kartik: Labeller Expertise Calculator.
- Kyle: Image Mask Service.
- Oleg: Refine backend for API reliability.
- Mathew: Enhance frontend interactivity.
Final Documentation (Rev 1) | April 2 | - Conduct end-to-end testing: | Finalize and submit SRS, V&V Plan, and test results. Complete user/admin manuals and deployment guide.
- Kartik and Kyle: Verify ML pipelines.
- Oleg: Test backend and database robustness.
- Mathew: Test UI for edge cases.